## Total Estimation
Project Name | Address Book
ILF | 7
EIF | 0
EO | 0
EQ | 4
EI | 4
Total Unadjusted Function Points | 15
Total GSC | 0.79
Total Adjusted Function Points | 11.85
Programmer can complete how much FP per day | 1.5
Total Man Days | 7.9
Phases | Percentage | Man Days
Requirement Gathering | 20 | 1.58
Technical Design | 20 | 1.58
Execution | 100 | 7.9
Testing | 5 | 0.395
Total Man Days |  | 11.455
Number of Developers |  | 2
Total Project Schedule |  | 5.7275

## ILF
Functionality | DET | RET | Value | Description
Address | 3 | 1 | 7 | Name,Phonenumber and Address
0
0
0

## EIF
Functionality | DET | RET | Value | Description
0

## EO
Functionality | FTR | RET | Value | Description
0

## EQ
Functionality | FTR | RET | Value | Description
AddressGrid Display | 1 | 4 | 4 | Addressgrid in the customer screen has four fields AddressID,Name,Phonenumber and Address

## EI
Functionality | FTR | RET | Value | Description
AddressBook Screen | 1 | 5 | 4 | Name,Address, PhoneNumber,Add and Cancel
0
0
0
0
0
0
0
0
0
0
0

## GSC
GSC Attribute | Definitions | Value
Data communications: | How many communication facilities are there to aid in the transfer or exchange of information with the application or system? | 1
Distributed data processing | How are distributed data and processing functions handled? | 1
Performance | Did the user require response time or throughput? | 1
Heavily used configuration | How heavily used is the current hardware platform where the application will be executed? | 1
Transaction rate | How frequently are transactions executed; daily, weekly, monthly, etc.? | 1
On-Line data entry | What percentage of the information is entered On-Line? | 1
End-user efficiency | Was the application designed for end-user efficiency? | 1
On-Line update | How many ILF’s are updated by On-Line transaction? | 1
Complex processing | Does the application have extensive logical or mathematical processing? | 1
Reusability | Was the application developed to meet one or many user’s needs? | 1
Installation ease | How difficult is conversion and installation? | 1
Operational ease | How effective and/or automated are start-up, back up, and recovery procedures? | 1
Multiple sites | Was the application specifically designed, developed, and supported to be installed at multiple sites for multiple organizations? | 1
Facilitate change | Was the application specifically designed, developed, and supported to facilitate change? | 1
GSC |  | 0.79

## Assumptions
Assumption Sections
Address book will not have huge traffic load. Maximum number of users at any point will not exceed 10
No backup mechanism is implemented.
No Audit history is implemented.
Concurrency measures are not taken care for the project.
Address book will be a windows based application
No login screen is provided for the application.
As the data is not critical no special security aspect is taken care for the application
Estimation only includes the software cost of the project any licenses or hardware has a different cost factor